## Datos
Nº of activities: | 8 | [7 empty] | Nº of duration risks: | 5
Nº Monte Carlo Simulations: | 20000 |  |  | RESET |  |  |  |  | Nº of cost risks: | 4
| Duration | [7 empty] | Cost | [18 empty] | R1 | R2 | R3 | R4 | R5
Activity | PDF | Cod. | µ | s | min | "+prob" | max | Slack | Variable cost | Fixed cost | s | min | "+prob" | max | Cod. | PDF |  | Precedents | A0 | A1 | A2 | A3 | A4 | A5 | A6 | A7 | A8 | A9 | A10 | A11 | A12 | A13 | Af
A1 | Normal | 3 | 2 | 0.4 | X | X | X | 0 | 755 | 0 | X | X | X | X | 1 | Deterministic |  | A0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A2 | Normal | 3 | 4 | 0.8 | X | X | X | 0 | 1150 | 0 | X | X | X | X | 1 | Deterministic |  | A1 | bar: A0
A3 | Normal | 3 | 7 | 1.2 | X | X | X | 0 | 630 | 0 | X | X | X | X | 1 | Deterministic |  | A2 | bar: A0
A4 | Normal | 3 | 3 | 0.4 | X | X | X | 0 | 916 | 0 | X | X | X | X | 1 | Deterministic |  | A3 | bar: A0
A5 | Normal | 3 | 6 | 1.25 | X | X | X | 0 | 840 | 0 | X | X | X | X | 1 | Deterministic |  | A4 | bar: R5 A13
A6 | Normal | 3 | 4 | 0.8 | X | X | X | 0 | 1250 | 0 | X | X | X | X | 1 | Deterministic |  | A5 | bar: R1 A9
A7 | Normal | 3 | 8 | 1.4 | X | X | X | 0 | 875 | 0 | X | X | X | X | 1 | Deterministic |  | A6 | bar: A3; R1 A9
A8 | Normal | 3 | 2 | 0.2 | X | X | X | 0 | 250 | 0 | X | X | X | X | 1 | Deterministic |  | A7 | bar: A4
A8 | bar: R3 A11
Activity | PDF | Cod. | µ | s | min | "+prob" | max | P / I | t / C | Risk/Act | Same Risk | [5 empty] | R1 | A9 | bar: A2
A9 | Uniform | 2 | X | X | 0.75 | X | 0.8 | P | t | R1 | a | [5 empty] | R2 | A10 | bar: A5
A9 | Uniform | 2 | X | X | 0.8 | X | 1 | I | 1750 | 2 | 0 | [5 empty] | R3 | A11 | bar: A6
A10 | Deterministic | 1 | 0.3 | X | X | X | X | P | t | R2 | b | [5 empty] | R4 | A12 | bar: A1
A10 | Deterministic | 1 | 5.5 | X | X | X | X | I | 840 | 5 | 0 | [5 empty] | R5 | A13 | bar: R4 A12
A11 | Deterministic | 1 | 0.05 | X | X | X | X | P | t | R3 | c | [6 empty] | Af | bar: A7 to A8; R2 A10
A11 | Uniform | 2 | X | X | 8 | X | 10 | I | 1250 | 6 | 0
A12 | Uniform | 2 | X | X | 0.6 | X | 0.8 | P | t | R4 | d
A12 | Uniform | 2 | X | X | 0.8 | X | 1 | I | 755 | 1 | 0
A13 | Triangular | 4 | X | X | 0.2 | 0.3 | 0.5 | P | t | R5 | e
A13 | Triangular | 4 | X | X | 0.4 | 0.5 | 0.8 | I | 755 | 1 | 0
Cost Risk1 | Deterministic | 1 | 0.3 | X | X | X | X | P | C | R6 | b
Cost Risk1 | Deterministic | 1 | 2000 | X | X | X | X | I | C | 5 | 0
Cost Risk2 | Uniform | 2 | X | X | 0.6 | X | 0.8 | P | C | R7 | d
Cost Risk2 | Deterministic | 1 | 2000 | X | X | X | X | I | C | 1 | 0
Cost Risk3 | Uniform | 2 | X | X | 0.7 | X | 0.8 | P | C | R8 | f
Cost Risk3 | Uniform | 2 | X | X | 2500 | X | 3500 | I | C | 4 | 0
Cost Risk4 | Uniform | 2 | X | X | 0.3 | X | 0.4 | P | C | R9 | g
Cost Risk4 | Uniform | 2 | X | X | 1500 | X | 2000 | I | C | 6 | 0
- In the RED-shaded cell, the VARIABLE DURATION corresponding to the activity affecting that duration risk must be entered.
- Each BLUE-shaded cell must enter the corresponding ACTIVITY number affected by this Duration and/or Cost risk.
- Identify with the original name of the risk (a, b,...) in the WHITE-shaded cell of the 'Same Risk' column. If the same risk can affect an activity's duration and cost simultaneously, designate these risks with the same letter (the original risk).
|  |  | Risk Correlation | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9
R1 | bar: R1; R3
R2 | bar: R2; R4
R3 | bar: R3
R4 | bar: R4
R5 | bar: R5
R6 | bar: R6
R7 | bar: R7
R8 | bar: R8
R9 | bar: R9
'1' means positive correlation (e.g. R5 will occur only if R2 occurs).
'-1' means negative correlation (e.g. R7 will occur only if R3 does NOT occur).
© Fernando Acebes Senovilla
Generate Activities
Generate Risks Duration
Generate Risks Cost

## Aux
Modelo | Cód | Coste | Cód
Deterministic | 1 | Deterministic | 1
Uniform | 2 | Uniform | 2
Normal | 3 | Normal | 3
Triangular | 4 | Triangular | 4
Beta-Pert | 5 | Beta-Pert | 5
Lognormal | 6
Buffer | 10